## POP Tracker
Site | Address | City | State | Site Code | Space Type | Eng Proposal # | Eng PO Status | Install Proposal # | Install PO Status | ENG Proposal | Plans Received | ENG PO | Axis Cam Layout | CAD Done | CAD Submitted (CW) | CAD Submitted (Colo) | Proposal | Proposal PO | Local Office Reviewed | Total Completion % | Current Step | Notes / Hold Reason
US-ATL03 | 180 Peachtree St, Atlanta, GA 30303, USA | Atlanta | GA | ATL03 | TBD | 301881 | No PO |  | No PO | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | Plans received | RFI
US-CHI01 | 350 E Cermak Rd, Chicago, IL 60616, USA | Chicago | IL | CHI01 | TBD | 301885 | No PO |  | No PO | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | Plans received | RFI
US-DAL01 | 1990 N Stemmons Fwy, Dallas, TX 75207, USA | Dallas | TX | DAL01 | TBD | 302561 | No PO |  | No PO | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | ENG PO | On hold - CoreWeave: waiting for the previous integrator to exit before we can access the site. No drawings exist yet. Engineering proposal to be queued once site access opens up.
US-DEN01 | 910 15th St, Denver, CO 80202, USA | Denver | CO | DEN01 | TBD | 301887 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans
Cage 0104 | 910 15th St, Denver, CO 80202, USA | Denver | CO | 0104 | CAGE | 301888 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans
US-LAX01 | 624 S Grand Ave, Los Angeles, CA 90017, USA | Los Angeles | CA | LAX01 | TBD | 301891 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans
US-PHL01 | 401 N Broad St, Philadelphia, PA 19108, USA | Philadelphia | PA | PHL01 | TBD | 298526 | PO Issued | 286822 | PO Issued | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 10 | 10 | 0 | 85 | CAD Submitted Colo | Waiting for Colo approval
US-QAS01 | 21715 Filigree Ct, Ashburn, VA 20147, USA | Ashburn | VA | QAS01 | TBD | 301893 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans
US-SEA01 | 2001 6th Ave #300, Seattle, WA 98121, USA | Seattle | WA | SEA01 | TBD | 302636 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans
US-SJC01 | 11 Great Oaks Blvd, San Jose, CA 95119, USA | San Jose | CA | SJC01 | TBD | 302565 | No PO |  | No PO | 10 | 10 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 30 | ENG PO | Waiting on ENG PO
US-UYK01 | 105 Enterprise Ave S, Secaucus, NJ 07094, USA | Secaucus | NJ | UYK01 | TBD | 302568 | No PO |  | No PO | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | Plans received | RFI
US-CHI02 | 350 E Cermak Road, Suite 355, Chicago, IL 60616, USA | Chicago | IL | CHI02 | TBD | 302638 | No PO |  | No PO | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | Plans received | RFI
US-DAL02 | 1990 N Stemmons Fwy, Dallas, TX 75207, USA | Dallas | TX | DAL02 | TBD | 301877 | No PO | 286824.1 | PO Issued | 10 | 10 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 60 | ENG PO | Waiting on ENG PO
US-PDX01 | 921 SW Washington St, Portland, OR 97205, USA | Portland | OR | PDX01 | TBD | 302571 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans
US-QTS01 | 335 Inverness Dr S, Englewood, CO 80112, USA | Englewood | CO | QTS01 | TBD | 302584 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans
US-SEA02 | 2001 6th Ave #350, Seattle, WA 98121, USA | Seattle | WA | SEA02 | TBD | 302637 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans
US-PLZ03 | 8375 Dominion Pkwy, Plano, TX 75024, USA | Plano | TX | PLZ03 | TBD | 302586 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans
US-RNE01 | 13600 Haslet Roanoke Rd, Roanoke, TX 76262, USA | Roanoke | TX | RNE01 | TBD | 302589 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans
Alliance Building | 13600 Haslet Roanoke Rd, Roanoke, TX 76262, USA | Roanoke | TX |  | TBD | 302595 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans
US-HOU01 | 660 Greens Pkwy, Houston, TX, USA | Houston | TX | HOU01 | TBD | 302599 | No PO |  | No PO | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | ENG PO | No plans

## Legend
Stage scoring (0 / 5 / 10)
0% (red) | Nothing exists at this stage yet
5% (yellow) | Requested but not received — RFI sent, or pending someone else's approval
10% (green) | Received / complete
PO status
PO Issued (green) | CoreWeave has issued a purchase order against this specific proposal
No PO (red) | No purchase order issued yet for this specific proposal
Two proposals per site
Engineering proposal | Covers the design/CAD scope
Installation proposal | Covers the actual POP build